## Project Plan: Genomic Analysis of COVID-19 Outcomes

Date: April 25, 2025

Team Solo: Jared Moore

### 1. Project Title

Genomic Correlates of COVID-19 Severity and Individual Risk

### 2. Project Goals and Objectives

This project aims to investigate genetic factors influencing COVID-19 severity and explore personalized risk assessment.

Objectives:

- Identify genes associated with varying COVID-19 outcomes using GenOMICC data.

- Compare a Personal Genome Project individual's genotype with these severity-associated alleles.

- Make a model to classify these alleles and how they relate to each other.

- Analyze potential gene matches from relevant papers and describe their function.

- Develop a system using a local LLM (DeepSeek) for users to query their potential genetic risk factors.

- Document the project, including the plan, workflow, and LLM integration.

### 3. Project Scope

This project will encompass:

- Downloading and processing genomic data from GenOMICC and the Personal Genome Project.

- Performing statistical analyses to identify correlations between genetic variations and COVID-19 outcomes.

- Annotating identified genes with functional information from literature.

- Setting up a local LLM for user queries.

- Developing user interaction instructions for the LLM.

- Writing an ACM-format report and creating a project summary presentation.

The project will focus on computational analysis of existing datasets and LLM integration, excluding wet-lab experiments or direct clinical data collection.

### 4. Background and Motivation

COVID-19 exhibits variable severity, with genetic factors playing a crucial role. Understanding these factors can provide insights into COVID-19 pathogenesis, identify high-risk individuals, and potentially inform personalized treatments. This project seeks to contribute by leveraging public genomic data and language models.

### 5. Methodology

The project will be conducted in five phases:

Phase 1: Data Acquisition and Preparation

- Download genomic data from GenOMICC and the Personal Genome Project.

- Process and format the data, including cleaning, quality control, and conversions.

- Set up the local environment with all dependencies.

Phase 2: Genomic Analysis

- Perform statistical analyses (e.g., GWAS) to identify genes associated with COVID-19 severity in GenOMICC data.

- Compare the Personal Genome Project participant's genotype with identified alleles.

- Identify potential risk and protective alleles.

Phase 3: Gene Annotation and Interpretation

- Review literature to gather information on genes identified in Phase 2.

- Annotate genes with their function, potential role in COVID-19, and relevant pathways.

- Summarize findings.

Phase 4: LLM Integration and Application

- Set up a local LLM (DeepSeek) and create a knowledge base from gene annotation data.

- Develop a method for users to query the LLM about genetic variants and their implications.

- Test and refine the LLM's responses.

Phase 5: Report and Presentation

- Write an ACM-format report documenting the project.

- Prepare and record a project summary presentation.

- Submit all deliverables.

### 6. Resources Required

- GenOMICC and Personal Genome Project data.

- Sufficient computational resources.

- Software: Python, LLM software (DeepSeek), and bioinformatics tools.

- Scientific literature access.

- ACM paper template, presentation software, and recording equipment.

### 7. Potential Challenges and Risks

- Data access and processing complexity.

- Data quality issues.

- Statistical analysis challenges.

- LLM integration complexity.

- Time constraints.

- Lack of significant findings.

- LLM limitations.

### 8. Mitigation Strategies

- Start data download early and explore cloud resources.

- Implement rigorous quality control.

- Consult experts on statistical methods.

- Begin LLM experimentation early.

- Develop a detailed timeline and prioritize tasks.

- Focus on methodology and learning, even with inconclusive results.

- Define LLM scope and acknowledge limitations.

### 9. Evaluation Plan

Project success will be evaluated based on:

- Completion of objectives.

- Thoroughness and accuracy of data analysis.

- Quality of gene annotation.

- Functionality and usability of LLM integration.

- Clarity and completeness of the report.

- Presentation effectiveness.

- Evidence of effort and learning.

Emphasis will be on the process, challenges, and mitigation, rather than solely on results.